## Team Backlog (Moving Car)
# | Task Name | Assignee | Task Status | Expected time to finish | Actual time to finish
1 | DIO Driver | Anas | Done | 2023-04-12 | 2023-04-11
2 | Interrupts Driver | Omar | Done | 2023-04-12 | 2023-04-11
3 | Timer 0 Driver | Mohab | Done | 2023-04-12 | 2023-04-12
4 | Timer 2 Driver | Mostafa | Done | 2023-04-12 | 2023-04-12
5 | Button Driver | Mohab | Done | 2023-04-12 | 2023-04-11
6 | LED Driver | Anas | Done | 2023-04-12 | 2023-04-12
7 | Motor Driver | Mostafa/Omar | Done | 2023-04-12 | 2023-04-11
8 | Application | Anas/Omar | Done | 2023-04-12 | 2023-04-12

## Data Validation Range (hidden)
Task Status
To Do
Doing
Done